## Sheet1
PROJECT_NUMBER | PROJECT_DESCRITPION | CATEGORY | PHASE | MILESTONE_DESIGN_START | MDS_STATUS | MILESTONE_DESIGN_COMPLETE | MDC_STATUS | MILESTONE_CONSTRUCTION_START | MCS_STATUS | MILESTONE_CONSTRUCTION_COMPLETE | MCC_STATUS
T6030227 | On-Board Audio Visual System | New York City Transit - Buses | Construction | 2017-05-01 | >6 month delay | 2018-01-01 | >6 month delay | 2018-06-01 | >6 month delay | 2024-05-01 | >6 month delay
T6030232 | On-Board Audio Visual System - Depot Wi-Fi | New York City Transit - Buses | Construction |  |  |  |  | 2016-03-01 | On Time | 2024-01-01 | >6 month delay
T7030213 | Automatic Passenger Counting - Pilot & Phase 1 | New York City Transit - Buses | Construction |  |  |  |  | 2017-10-01 | On Time | 2024-12-01 | >6 month delay
T7030215 | Automatic Vehicle Location Monitoring (AVLM) for Paratransit Vehicles | New York City Transit - Buses | Construction | 2017-09-01 | On Time | 2018-10-01 | On Time | 2018-10-01 | On Time | 2024-04-01 | >6 month delay
T7030216 | Purchase 45 Standard Electric Buses | New York City Transit - Buses | Construction | 2019-03-01 | On Time | 2021-12-01 | >6 month delay | 2021-12-01 | >6 month delay | 2024-09-01 | >6 month delay
T7030224 | All-Electric Bus (AEB) Chargers for 5 Bus Depots | New York City Transit - Buses | Construction |  |  |  |  | 2021-03-01 | On Time | 2024-05-01 | >6 month delay
T8030203 | Purchase 90 Articulated Electric Buses | New York City Transit - Buses | Construction |  |  |  |  | 2024-02-01 | 4-6 month delay | 2026-01-01
T8030204 | Purchase 224 Articulated Buses | New York City Transit - Buses | Construction |  |  |  |  | 2023-12-01 | 4-6 month delay | 2025-11-01 | 4-6 month delay
T8030205 | Purchase 92 Express Buses | New York City Transit - Buses | Planning |  |  |  |  | 2024-06-01 |  | 2027-06-01
T8030213 | Purchase 15 Standard Battery Electric Buses | New York City Transit - Buses | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-09-01 | >6 month delay
T8030215 | Purchase 5 Standard Battery Electric Buses | New York City Transit - Buses | Construction | 2022-03-01 | On Time | 2022-08-01 | On Time | 2022-09-01 | On Time | 2024-09-01 | On Time
T8030218 | Automated Passenger Counting, Phase 2 | New York City Transit - Buses | Construction |  |  |  |  | 2022-09-01 | On Time | 2024-09-01 | On Time
T8030219 | Battery Electric Bus Charging Infrastructure: Jamaica Gantries | New York City Transit - Buses | Construction |  |  |  |  | 2022-12-01 | On Time | 2027-07-01 | >6 month delay
T6120403 | Replacement of Bus Radio System | New York City Transit - Depots | Construction | 2006-07-01 | On Time | 2014-04-01 | >6 month delay | 2012-02-01 | On Time | 2024-08-01 | >6 month delay
T6120444 | New East New York (ENY) Tower - NYCT | New York City Transit - Depots | Construction | 2006-07-01 |  | 2024-08-01 |  | 2018-12-01 | On Time | 2024-08-01 | >6 month delay
T6120445 | CAD/AVL & Secure Bus Access (SBA) | New York City Transit - Depots | Planning |  |  |  |  | 2024-06-01 | >6 month delay
T7120306 | Replace Emergency Generator at Yukon Depot | New York City Transit - Depots | Construction | 2017-06-01 | On Time | 2019-08-01 | On Time | 2020-03-01 | On Time | 2024-02-01 | >6 month delay
T7120321 | Facade Repair and Window Replacement at East New York Depot | New York City Transit - Depots | Construction |  |  |  |  | 2020-03-01 | On Time | 2024-03-01 | >6 month delay
T7120403 | Select Bus Service 2015-19 | New York City Transit - Depots | Construction | 2018-05-01 | On Time | 2018-12-01 | On Time | 2016-02-01 | On Time | 2024-12-01 | >6 month delay
T7120404 | Traffic Signal Priority - Phase 2 | New York City Transit - Depots | Construction |  |  |  |  | 2017-10-01 | On Time | 2024-06-01 | >6 month delay
T8120303 | Jamaica Depot Reconstruction | New York City Transit - Depots | Construction | 2019-07-01 | On Time | 2022-03-01 | On Time | 2022-12-01 | On Time | 2027-07-01 | >6 month delay
T8120304 | Roof Topping & Expansion Joint Replacement at Michael J Quill Depot | New York City Transit - Depots | Construction | 2017-08-01 | On Time | 2019-12-01 | On Time | 2022-12-01 | On Time | 2024-01-01 | On Time
T8120306 | Zero Emission Fleet Transformation Study | New York City Transit - Depots | Design | 2022-02-01 | On Time | 2026-03-01 | On Time
T8120307 | Jamaica Depot: Construct Bus Parking Lot at York College | New York City Transit - Depots | Construction |  |  |  |  | 2022-12-01 | On Time | 2027-07-01 | >6 month delay
T8120405 | Automated Bus Lane Enforcement (ABLE), Ph 2A (300 Buses) | New York City Transit - Depots | Construction |  |  |  |  | 2022-07-01 | On Time | 2024-01-01 | >6 month delay
T8120409 | Chassis Wash Replacement at Tuskegee Airmen Depot (SBMP) | New York City Transit - Depots | Construction |  |  |  |  | 2022-12-01 | On Time | 2024-01-01 | On Time
T8120410 | Bus Radio System (Additional Support) | New York City Transit - Depots | Construction |  |  |  |  | 2016-03-01 | On Time | 2024-08-01 | >6 month delay
T8120412 | Automated Camera Enforcement (ACE), Phase 2B | New York City Transit - Depots | Construction |  |  |  |  | 2023-12-01 |  | 2024-12-01
T7060506 | Rehabilitation of Vent Plant at Forsyth Street on the 6th Avenue Line | New York City Transit - Line Equipment | Construction | 2016-02-01 | On Time | 2018-05-01 | On Time | 2018-12-01 | On Time | 2024-06-01 | >6 month delay
T8060514 | Fan Plant SCADA Head-End Upgrade | New York City Transit - Line Equipment | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-08-01 | On Time
T8060518 | Tunnel Lighting on the 8 Avenue Line | New York City Transit - Line Equipment | Construction |  |  |  |  | 2022-05-01 | On Time | 2024-08-01 | On Time
T8060519 | Fiber Optic Cable on the 8 Avenue Line | New York City Transit - Line Equipment | Construction |  |  |  |  | 2022-05-01 | On Time | 2024-08-01 | On Time
T8060521 | Rehab Pump Room at Willoughby Street on the Broadway Line | New York City Transit - Line Equipment | Construction |  |  |  |  | 2022-12-01 | On Time | 2024-06-01 | 4-6 month delay
T8060522 | Rehab Pump Room at Adams Street on the Broadway Line | New York City Transit - Line Equipment | Construction |  |  |  |  | 2022-12-01 | On Time | 2024-06-01 | 4-6 month delay
T8060523 | Rehab Pump Room at Rockwell Place on the 4 Avenue Line | New York City Transit - Line Equipment | Construction |  |  |  |  | 2023-12-01 |  | 2025-12-01
T8060524 | Deep Wells Back-Flushing on the Fulton and Crosstown Lines | New York City Transit - Line Equipment | Construction |  |  |  |  | 2023-12-01 |  | 2025-05-01
T8060526 | Sandy Mitigation: Pump Room Enhancements | New York City Transit - Line Equipment | Construction |  |  |  |  | 2023-12-01 |  | 2026-10-01
T8060527 | Sandy Mitigation: 4 Pump Rooms (Jerome-Pelham Tube) | New York City Transit - Line Equipment | Construction |  |  |  |  | 2023-12-01 |  | 2026-04-01
T8060528 | Sandy Mitigation: Duct Seals at 2 Fan Plants | New York City Transit - Line Equipment | Construction |  |  |  |  | 2023-12-01 |  | 2026-04-01
T7070301 | Structural Rehabilitation from Boston Road to East 180th Street Abutment on White Plains Road Line | New York City Transit - Line Structures | Construction | 2014-07-01 | On Time | 2015-07-01 | On Time | 2022-05-01 | >6 month delay | 2025-01-01 | >6 month delay
T7070308 | Rehabilitation of Emergency Exits at Various Locations | New York City Transit - Line Structures | Construction | 2017-01-01 | On Time | 2021-10-01 | >6 month delay | 2018-04-01 | On Time | 2024-06-01 | >6 month delay
T7070310 | Overcoat Painting and Steel Repairs at 17 Bridges on the Dyre Line | New York City Transit - Line Structures | Construction | 2015-01-01 | On Time | 2016-09-01 | On Time | 2022-05-01 | >6 month delay | 2025-01-01 | >6 month delay
T7070324 | Line Structure Component Repairs in Uptown Manhattan and Queens on the Lexington, Queens Boulevard and Crosstown Lines - Design Only | New York City Transit - Line Structures | Design | 2016-02-01 | On Time | 2024-12-01 | >6 month delay
T7070325 | Line Structure Component Repairs on the Culver and Brighton Lines - Design Only | New York City Transit - Line Structures | Design | 2016-06-01 | On Time | 2024-09-01 | >6 month delay
T7070345 | Rehabilitation of the Culver Line Viaduct Additional Work - Design Only | New York City Transit - Line Structures | Design | 2023-01-01 | On Time | 2024-06-01
T7070351 | Rehabilitate Two Westchester Avenue Bridges on the Pelham Line - Design Only | New York City Transit - Line Structures | Design | 2023-01-01 | >6 month delay | 2024-06-01 | >6 month delay
T7070355 | Lower Level Structure Repairs at Nevins Street Station on the Eastern Parkway Line - Design Only | New York City Transit - Line Structures | Design | 2020-10-01 | On Time | 2024-06-01 | >6 month delay
T7070357 | Overcoat Painting at East 180 Street Flyover on the Dyre Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-05-01 | On Time | 2025-01-01 | On Time
T8070312 | Line Structure Component Repairs on the Canarsie Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2021-12-01 | On Time | 2025-03-01 | On Time
T8070317 | Overcoat Painting: 48 St to 72 St on the Flushing Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-09-01 | On Time | 2025-05-01 | On Time
T8070318 | Line Structure Component Repairs on the Concourse Line | New York City Transit - Line Structures | Construction | 2015-10-01 | On Time | 2019-05-01 | On Time | 2021-12-01 | On Time | 2024-03-01 | On Time
T8070319 | Vents Between Stations: East 161 Street to East 192 Street on the Concourse Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-03-01 | On Time
T8070323 | Replace Electrical and Mechanical Equipment at South Channel Bridge on the Rockaway Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-08-01 | On Time
T8070324 | Rehab Hammels Wye on the Rockaway Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-08-01 | On Time
T8070325 | Elevated Structure Repairs: Over-Land Sections on the Rockaway Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-08-01 | On Time
T8070326 | Line Structure Component Repairs on the Jamaica Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-04-01 | 4-6 month delay
T8070327 | Line Structure Component Repairs on the 63 Street Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-04-01 | 4-6 month delay
T8070329 | Line Structure Component Repairs on the 8 Avenue Line (Downtown Manhattan) | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-05-01 | On Time | 2024-08-01 | On Time
T8070331 | Structure Repairs: 61 Street-Woodside on the Flushing Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-09-01 | On Time | 2025-05-01 | On Time
T8070332 | Repair Abutment Wall: Coney Island Yard | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2024-09-01 | On Time
T8070333 | Replace Bridge: St Marks Avenue on the Franklin Avenue Shuttle | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2024-09-01 | On Time
T8070334 | Rehabilitation of Emergency Exits at 12 Locations | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-02-01 | On Time | 2024-09-01 | On Time
T8070335 | Overcoat Painting: Myrtle Avenue to DeSales Place on the Jamaica Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-03-01 | On Time
T8070336 | Overcoat Painting: Williamsburg Bridge to Myrtle Avenue on the Jamaica Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-03-01 | On Time
T8070337 | Overcoat Painting: East New York Leads & Loops | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-03-01 | On Time
T8070341 | Demolition of Abandoned Structures on the White Plains Road Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-05-01 | On Time | 2025-01-01 | On Time
T8070342 | Demolition of Abandoned Structures on the Jamaica Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-11-01 | 4-6 month delay
T8070344 | Overcoat Painting: Kings Highway to West 8 Street on the Culver Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-04-01 | On Time
T8070345 | Elevated Structure Repairs: Portal to Kings Highway on the Culver Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2022-12-01 | On Time | 2024-11-01 | On Time
T8070347 | Demolition of Abandoned Structures: Signal Tower on the Jamaica Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2023-12-01 |  | 2026-03-01
T8070348 | Overcoat Painting: Myrtle Line Outstanding Work | New York City Transit - Line Structures | Construction |  |  |  |  | 2023-12-01 |  | 2026-05-01
T8070354 | Line Structure Component Repairs on the Lexington and Jerome Lines | New York City Transit - Line Structures | Construction |  |  |  |  | 2023-12-01 |  | 2026-03-01
T8070355 | Rehabilitation of Emergency Exits at Various Locations | New York City Transit - Line Structures | Construction |  |  |  |  | 2023-07-01 |  | 2025-06-01
T8070356 | Line Structure Component Repairs at East Broadway on the 6 Avenue Line | New York City Transit - Line Structures | Construction |  |  |  |  | 2023-05-01 |  | 2024-12-01
T6160402 | NYCT-Wide Storage Area Network/Disaster Recovery | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2011-12-01 | On Time | 2024-05-01 | >6 month delay
T6160705 | Rehab Employee Facility at Chambers St on the Nassau Line | New York City Transit - Misc./Emergency | Construction | 2012-08-01 | >6 month delay | 2018-11-01 | >6 month delay | 2020-02-01 | >6 month delay | 2024-03-01 | >6 month delay
T7160207 | Capital Revolving Fund 2019 | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2019-03-01 | On Time | 2026-04-01 | >6 month delay
T7160512 | Test Pits | New York City Transit - Misc./Emergency | Construction | 2016-09-01 | On Time | 2017-03-01 | On Time | 2018-04-01 | On Time | 2024-04-01 | >6 month delay
T7160723 | Priority Repairs of Tiffany Central Warehouse Exterior Walls | New York City Transit - Misc./Emergency | Construction | 2017-04-01 | On Time | 2017-12-01 | On Time | 2022-03-01 | >6 month delay | 2024-05-01 | >6 month delay
T7160727 | Replacement of Roof at Tiffany Central Warehouse | New York City Transit - Misc./Emergency | Construction | 2017-10-01 | On Time | 2021-11-01 | >6 month delay | 2022-03-01 | >6 month delay | 2024-05-01 | >6 month delay
T8160208 | Capital Revolving Fund 2021 | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2021-04-01 | On Time | 2026-04-01 | On Time
T8160209 | Capital Revolving Fund 2022 | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2022-01-01 | On Time | 2026-12-01 | On Time
T8160403 | Improved Resiliency of RCC Critical Systems | New York City Transit - Misc./Emergency | Design | 2024-03-01 | >6 month delay
T8160517 | Concrete Cylinder Testing | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2018-10-01 | On Time | 2024-03-01 | 4-6 month delay
T8160518 | Concrete Batch Plant Inspection | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2018-10-01 | On Time | 2024-03-01 | 4-6 month delay
T8160605 | Consultant Services: Underground Storage Tank (UST) Remediation | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-12-01 | On Time
T8160606 | Fire Alarms and Sprinklers: Various Locations | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2023-12-01 |  | 2027-11-01
T8160705 | Improvements to Electrical and Mechanical Systems at Livingston Plaza - Phase B | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-06-01 | 4-6 month delay
T8160706 | EMD Employee Facility at Hoyt-Schermerhorn Station on the Fulton Line | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2020-12-01 | On Time | 2024-03-01 | >6 month delay
T8160711 | Employee Facility Consolidation at 2 Avenue Station on the 6th Avenue Line | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-05-01 | >6 month delay
T8160712 | Rehabilitation of Employee Bathroom and Breakroom Facilities at Various Locations, Phase 3 | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2023-05-01 |  | 2024-05-01
T8160714 | Employee Facility Repairs at Station Component Locations | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2023-10-01 |  | 2025-08-01
T8160715 | Perimeter Hardening: Power Control Center (SBMP) | New York City Transit - Misc./Emergency | Construction | 2022-08-01 |  | 2023-05-01 |  | 2023-12-01 |  | 2024-10-01
T8160716 | Employee Facility Expansion at 7 Avenue Station on the 6 Avenue Line | New York City Transit - Misc./Emergency | Construction |  |  |  |  | 2023-12-01 |  | 2025-06-01
T8160717 | Water Condition Survey at West 4 Street Station on the 8 Avenue Line | New York City Transit - Misc./Emergency | Design | 2024-05-01 |  | 2024-08-01
T6040405 | New Fare Payment System - OMNY | New York City Transit - Passenger Stations | Construction | 2013-12-01 | >6 month delay | 2018-02-01 | >6 month delay | 2017-11-01 | >6 month delay | 2025-03-01 | >6 month delay
T6041307 | ADA Accessibility at 68 St-Hunter College Station on the Lexington Av Line | New York City Transit - Passenger Stations | Construction | 2010-04-01 | On Time | 2016-09-01 | >6 month delay | 2021-12-01 | >6 month delay | 2024-12-01 | >6 month delay
T6041323 | ADA Accessibility at 8th Avenue Station on the Sea Beach Line (Southbound) | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-09-01 | On Time
T7040401 | New Fare Payment System - OMNY, Phase 2 | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2017-11-01 | On Time | 2025-03-01 | >6 month delay
T7040707 | Replace 7 Escalators at Various Locations in the Bronx and Manhattan | New York City Transit - Passenger Stations | Construction | 2017-05-01 | On Time | 2019-04-01 | On Time | 2021-11-01 | >6 month delay | 2024-09-01 | On Time
T7040713 | Replace 5 Escalators at Various Locations in Brooklyn and Manhattan | New York City Transit - Passenger Stations | Construction | 2017-11-01 | On Time | 2019-07-01 | On Time | 2021-11-01 | >6 month delay | 2024-09-01 | On Time
T7041210 | Renewal of 111 Street Station on the Flushing Line | New York City Transit - Passenger Stations | Construction | 2016-12-01 | On Time | 2019-09-01 | On Time | 2023-01-01 | >6 month delay | 2026-01-01 | On Time
T7041211 | Renewal of 103 Street-Station Corona Plaza on the Flushing Line | New York City Transit - Passenger Stations | Construction | 2016-12-01 | On Time | 2019-09-01 | On Time | 2023-01-01 | >6 month delay | 2026-01-01 | On Time
T7041212 | Renewal of 82 Street Station-Jackson Heights on the Flushing Line | New York City Transit - Passenger Stations | Construction | 2016-12-01 | On Time | 2019-09-01 | On Time | 2023-01-01 | >6 month delay | 2026-01-01 | On Time
T7041213 | Renewal of Woodhaven Boulevard Station on the Jamaica Line | New York City Transit - Passenger Stations | Construction | 2017-10-01 | On Time | 2020-06-01 | On Time | 2021-12-01 | >6 month delay | 2024-09-01 | >6 month delay
T7041214 | Renewal of 85 Street-Forest Parkway on the Jamaica Line | New York City Transit - Passenger Stations | Construction | 2017-10-01 | On Time | 2020-06-01 | On Time | 2022-12-01 | >6 month delay | 2025-11-01 | >6 month delay
T7041215 | Renewal of 75 Street-Elderts Lane on the Jamaica Line | New York City Transit - Passenger Stations | Construction | 2017-10-01 | On Time | 2020-06-01 | On Time | 2022-12-01 | >6 month delay | 2025-06-01 | >6 month delay
T7041216 | Renewal of Cypress Hills Station on the Jamaica Line | New York City Transit - Passenger Stations | Construction | 2017-10-01 | On Time | 2020-06-01 | On Time | 2022-12-01 | >6 month delay | 2025-11-01 | >6 month delay
T7041217 | Renewal of 69 Street Station on the Flushing Line | New York City Transit - Passenger Stations | Construction | 2016-12-01 | On Time | 2019-09-01 | On Time | 2023-01-01 | >6 month delay | 2026-01-01 | On Time
T7041218 | Renewal of 61 Street Station-Woodside on the Flushing Line | New York City Transit - Passenger Stations | Construction | 2016-12-01 | On Time | 2020-04-01 | On Time | 2022-09-01 | >6 month delay | 2025-05-01 | On Time
T7041219 | Renewal of 52 Street Station on the Flushing Line | New York City Transit - Passenger Stations | Construction | 2016-12-01 | On Time | 2019-09-01 | On Time | 2023-01-01 | >6 month delay | 2026-01-01 | On Time
T7041251 | Repair of Platform Components at 5 Locations on the Canarsie Line | New York City Transit - Passenger Stations | Construction | 2015-12-01 | On Time | 2021-05-01 | >6 month delay | 2018-10-01 | On Time | 2025-03-01 | >6 month delay
T7041275 | Ventilator Repairs at Various Locations | New York City Transit - Passenger Stations | Construction | 2021-10-01 | On Time | 2023-11-01 | On Time | 2020-08-01 | On Time
T70412F4 | Repair Subway Street Stairs at 14 Street on the 6 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | >6 month delay | 2025-03-01 | >6 month delay
T70412L2 | Platform Component Repairs at 14th Street on the 6th Avenue Line | New York City Transit - Passenger Stations | Construction | 2019-08-01 | On Time | 2021-05-01 | >6 month delay | 2021-12-01 | >6 month delay | 2025-03-01 | >6 month delay
T7041314 | ADA Accessibility at Court Square Station on the Crosstown Line | New York City Transit - Passenger Stations | Construction | 2018-03-01 | On Time | 2020-07-01 | On Time | 2021-12-01 | >6 month delay | 2024-09-01 | On Time
T7041315 | ADA Accessibility at 149 Street-Grand Concourse Complex | New York City Transit - Passenger Stations | Construction | 2018-06-01 | On Time | 2019-03-01 | On Time | 2020-08-01 | On Time | 2024-12-01 | >6 month delay
T7041316 | ADA Accessibility at Woodhaven Boulevard Station on the Jamaica Line | New York City Transit - Passenger Stations | Construction | 2018-11-01 | On Time | 2020-06-01 | On Time | 2021-12-01 | >6 month delay | 2024-09-01 | >6 month delay
T7041322 | ADA Accessibility at 95 St Station on the 4th Avenue Line | New York City Transit - Passenger Stations | Construction | 2019-05-01 | On Time | 2022-08-01 | >6 month delay | 2022-12-01 | >6 month delay | 2025-06-01 | >6 month delay
T7041324 | ADA Accessibility at 68 St-Hunter College Station on the Lexington Av Line | New York City Transit - Passenger Stations | Construction | 2010-04-01 | On Time | 2016-09-01 | On Time | 2021-12-01 | >6 month delay | 2024-12-01 | >6 month delay
T7041327 | ADA Accessibility and Station Improvements at Westchester Square Station on the Pelham Line | New York City Transit - Passenger Stations | Construction | 2018-10-01 | On Time | 2019-10-01 | On Time | 2021-12-01 | >6 month delay | 2024-09-01 | >6 month delay
T7041330 | ADA Accessibility Design and New Stair at 14 Street - 6 Avenue / 7 Avenue Station Complex | New York City Transit - Passenger Stations | Construction | 2018-06-01 | On Time | 2021-05-01 | >6 month delay | 2021-12-01 | On Time | 2025-03-01 | On Time
T7041335 | ADA Accessibility at Queensboro Plaza on the Flushing Line | New York City Transit - Passenger Stations | Construction | 2018-11-01 | On Time | 2020-01-01 | On Time | 2021-12-01 | >6 month delay | 2024-09-01 | >6 month delay
T7041338 | ADA Accessibility at Tremont Avenue on the Concourse Line | New York City Transit - Passenger Stations | Construction | 2019-03-01 | On Time | 2019-12-01 | On Time | 2020-08-01 | On Time | 2024-12-01 | >6 month delay
T7041341 | ADA Accessibility at Neptune Ave on the Culver Line - Design Only | New York City Transit - Passenger Stations | Design | 2024-02-01 | >6 month delay | 2024-05-01 | >6 month delay
T7041342 | ADA Accessibility at Ave I on the Culver Line - Design Only | New York City Transit - Passenger Stations | Design | 2023-08-01 | >6 month delay | 2024-03-01 | 4-6 month delay
T7041346 | ADA Accessibility at 6 Avenue Station on the Canarsie Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | >6 month delay | 2025-03-01 | >6 month delay
T7041347 | ADA Accessibility at 14 Street Station on the 6 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | >6 month delay | 2025-03-01 | >6 month delay
T7041348 | ADA Accessibility at 14 Street Station on the Broadway-7 Avenue Line | New York City Transit - Passenger Stations | Construction | 2018-11-01 | On Time | 2021-05-01 | On Time | 2021-12-01 | >6 month delay | 2025-03-01 | >6 month delay
T7041402 | Access Improvements: Grand Central, Phase 2 | New York City Transit - Passenger Stations | Construction | 2016-05-01 | On Time | 2021-09-01 | >6 month delay | 2016-09-01 | On Time | 2025-08-01 | >6 month delay
T8040405 | Additional Work: Fare Collection | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2017-11-01 | On Time | 2025-03-01 | On Time
T8040708 | Replace 5 Hydraulic Elevators at 2 Locations on the Jamaica Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-09-01 | On Time
T8040709 | Replace 4 Escalators at 2 Locations on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-09-01 | On Time | 2025-05-01 | On Time
T8040711 | Replace 4 Escalators at 2 Locations on 4 Ave and Concourse Lines | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2025-01-01 | >6 month delay
T8040712 | Replace 17 Escalators at 6 Locations on Various Lines | New York City Transit - Passenger Stations | Construction | 2020-09-01 | On Time | 2022-03-01 | On Time | 2022-08-01 | On Time | 2026-08-01 | On Time
T8040713 | Replace 8 Escalators at Grand Central on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2025-08-01 | On Time
T8040714 | Replace 3 Escalators at Broadway Junction on the Fulton Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2027-09-01
T8040715 | Replace 14 Elevators at 5 Locations | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-09-01 | On Time
T8040716 | Replace 6 Escalators at 2 Locations | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-08-01 | On Time
T8040717 | Replace 19 Elevators at Various Locations | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-10-01 | On Time
T8040718 | Replace 1 Escalator at Parkchester on the Pelham Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-06-01 | On Time
T8040719 | Replace 17 Elevators at 8 Stations | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-09-01
T8040720 | Replace 20 Elevators at 9 Stations | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-09-01
T8040721 | Replace 21 Escalators At 6 Stations | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-11-01
T8041209 | Livonia Av-Junius St Station Connector | New York City Transit - Passenger Stations | Construction | 2021-08-01 | On Time | 2022-06-01 | On Time | 2022-12-01 | >6 month delay | 2026-09-01 | >6 month delay
T8041217 | Platform Components: 2 Locations on the Queens Boulevard Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-11-01 | On Time | 2024-03-01 | 4-6 month delay
T8041218 | Platform Components: 5 Locations on the Broadway-7 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-03-01 | On Time | 2024-10-01 | On Time
T8041221 | Ventilator Repairs at 8 Ave on the Canarsie Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2025-03-01 | On Time
T8041223 | Ventilator Repairs at 3 Locations in Manhattan and the Bronx | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-07-01 | On Time | 2024-07-01 | On Time
T8041224 | Station Renewal: Borough Hall on the Lexington Avenue Line | New York City Transit - Passenger Stations | Construction | 2014-10-01 | On Time | 2022-06-01 | On Time | 2022-12-01 | On Time | 2025-04-01 | On Time
T8041225 | Platform Components: 68 St - Hunter College on the Lexington Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-12-01 | On Time
T8041226 | Ventilator Repairs at Grand Central on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2025-08-01 | On Time
T8041227 | Platform Components: 137 Street on the Broadway-7 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-06-01 | On Time
T8041229 | Platform Components: 6 Avenue on the Canarsie Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2025-03-01 | On Time
T8041230 | Platform Components: 14 Street on the 6 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2025-03-01 | On Time
T8041231 | Platform Components: Metropolitan Ave on the Crosstown Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-02-01 | >6 month delay
T8041232 | Station Renewal: Woodhaven Boulevard on the Jamaica Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-09-01 | On Time
T8041234 | Platform Components: Broadway Junction on the Jamaica Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2027-09-01
T8041235 | Ventilator Repairs at 4 Locations in Manhattan | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-02-01 | On Time | 2025-02-01 | On Time
T8041239 | Grand Central: Center Core East on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-05-01 | On Time
T8041240 | Grand Central: Widening Stairs U2/U6 on the Lexington Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-05-01 | On Time
T8041243 | Station Renewal: 111 Street on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-01-01 | On Time | 2026-01-01 | On Time
T8041244 | Station Renewal: 103 Street-Corona Plaza on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-01-01 | On Time | 2026-01-01 | On Time
T8041245 | Station Renewal: 82 Street-Jackson Heights on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-01-01 | On Time | 2026-01-01 | On Time
T8041246 | Station Renewal: 69 Street on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-01-01 | On Time | 2026-01-01 | On Time
T8041247 | Station Renewal: 52 Street on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-01-01 | On Time | 2026-01-01 | On Time
T8041249 | Platform Edges: 2 Locations on the Jamaica Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-11-01 | 4-6 month delay
T8041250 | Station Renewal: 85 Street-Forest Parkway on the Jamaica Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-11-01 | 4-6 month delay
T8041251 | Station Renewal: 75 Street-Elderts Lane on the Jamaica Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-11-01 | 4-6 month delay
T8041252 | Station Renewal: Cypress Hills on the Jamaica Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-11-01 | 4-6 month delay
T8041254 | Ventilator Repairs at 4 Locations in Brooklyn | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-10-01 | On Time | 2025-06-01 | On Time
T8041256 | Platform Components: New Lots Avenue on the New Lots Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041257 | Station Renewal: 242 Street on the Broadway-7 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041258 | Station Renewal: 61 Street-Woodside on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-09-01 | On Time | 2025-05-01 | On Time
T8041259 | Station Components: 46 Street-Bliss Street on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041260 | Stormwater Mitigation: Street Stairs Package 1 | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-06-01 |  | 2024-06-01
T8041262 | Platform Components: 111 Street on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-01-01 | On Time | 2026-01-01 | On Time
T8041269 | Water Condition Remedy - 2023 | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2025-12-01
T8041277 | Ventilator Repairs at 3 Locations in Manhattan | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2024-12-01
T8041278 | Ventilator Repairs at 3 Locations in Queens | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-11-01 |  | 2025-06-01
T8041280 | Stormwater Mitigation: Cortlandt Street | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2024-02-01 |  | 2025-10-01
T8041282 | Comm and Security Upgrades at Sutphin Blvd-Archer Ave | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-10-01 |  | 2024-10-01
T8041283 | Track Wall Tiles at 14 Street on the Broadway-7 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2024-01-01 |  | 2024-08-01
T8041302 | ADA Accessibility at 96 Street on the 8 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041303 | ADA Accessibility at Dyckman Street (northbound) on the Broadway-7 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2020-12-01 | On Time | 2024-02-01 | >6 month delay
T8041304 | ADA Accessibility at 6 Avenue on the Canarsie Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2025-03-01 | On Time
T8041305 | ADA Accessibility at 14 Street on the Broadway-7 Ave Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2025-03-01 | On Time
T8041306 | ADA Accessibility at 86 Street on the Lexington Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041309 | ADA Accessibility at 81 Street on the 8 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041311 | ADA Accessibility at Borough Hall on the Lexington Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-04-01 | On Time
T8041312 | ADA Accessibility at Junius Street on the New Lots Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-09-01 | On Time
T8041314 | ADA Accessibility at Sheepshead Bay on the Brighton Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-09-01 | On Time
T8041317 | ADA Accessibility at Grand Street on the Canarsie Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2020-12-01 | On Time | 2024-02-01 | >6 month delay
T8041319 | ADA Accessibility at 7 Avenue on the 6 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2020-12-01 | On Time | 2024-02-01 | >6 month delay
T8041321 | ADA Accessibility at Kings Highway on the Culver Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-09-01 | On Time
T8041322 | ADA Accessibility at Classon Avenue on the Crosstown Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041323 | ADA Accessibility at New Lots Avenue on the New Lots Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041326 | ADA Accessibility at 36 Street on the 4 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041327 | ADA Accessibility at Lorimer Street on the Canarsie Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2020-12-01 | On Time | 2024-02-01 | 4-6 month delay
T8041328 | ADA Accessibility at Metropolitan Ave on the Crosstown Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2020-12-01 | On Time | 2024-02-01 | 4-6 month delay
T8041329 | ADA Accessibility at Woodhaven Boulevard on the Jamaica Line | New York City Transit - Passenger Stations | Construction | 2018-11-01 | On Time | 2020-06-01 | On Time | 2021-12-01 | On Time | 2024-09-01 | On Time
T8041330 | ADA Accessibility and Station Improvements at Westchester Square on the Pelham Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-09-01 | On Time
T8041331 | ADA Accessibility at Parkchester-East 177 Street on the Pelham Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-06-01 | On Time
T8041332 | ADA Accessibility at East 149 Street on the Pelham Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2020-12-01 | On Time | 2024-02-01 | >6 month delay
T8041333 | ADA Accessibility at Mosholu Parkway on the Jerome Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-09-01 | On Time
T8041334 | ADA Accessibility at 242 Street on the Broadway-7 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041336 | ADA Accessibility at Rockaway Boulevard on the Liberty Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-09-01 | On Time
T8041337 | ADA Accessibility at Beach 67 Street on the Far Rockaway Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2020-12-01 | On Time | 2024-02-01 | >6 month delay
T8041338 | ADA Accessibility at Woodhaven Boulevard on the Queens Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-09-01 | On Time
T8041339 | ADA Accessibility at Steinway Street on the Queens Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-09-01 | On Time
T8041341 | ADA Accessibility at Broadway on the Astoria Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041345 | ADA Accessibility at 181 Street on the 8 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-09-01 | On Time
T8041346 | ADA Accessibility at Broadway Junction Complex | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2027-09-01
T8041347 | ADA Accessibility at Northern Boulevard on the Queens Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-06-01 | On Time
T8041348 | ADA Accessibility at Church Avenue on the Brighton Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-09-01 | On Time
T8041349 | ADA Accessibility at 33 Street-Rawson Street on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041352 | ADA Accessibility at 46 Street-Bliss Street on the Flushing Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041371 | ADA Accessibility at 137 Street on the Broadway-7 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-06-01 | On Time
T8041372 | ADA Accessibility at Harlem 148 Street on the Lenox Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041373 | ADA Accessibility at Court Square-23 Street on the Queens Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8041375 | ADA Accessibility at 95 Street on the 4 Avenue Line | New York City Transit - Passenger Stations | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-06-01 | On Time
T7130207 | Purchase 27 Refuse Flats - Design Only | New York City Transit - Service Vehicles | Design | 2014-05-01 | On Time | 2024-12-01 | >6 month delay
T7130208 | Purchase 12 3-Ton Crane Cars | New York City Transit - Service Vehicles | Construction | 2014-05-01 | On Time | 2020-07-01 | On Time | 2020-07-01 | On Time | 2024-12-01 | >6 month delay
T7130211 | Purchase Locomotives | New York City Transit - Service Vehicles | Construction | 2014-05-01 | On Time | 2020-08-01 | 4-6 month delay | 2020-08-01 | 4-6 month delay | 2025-10-01 | On Time
T7130213 | Purchase Various Non-Revenue Vehicles | New York City Transit - Service Vehicles | Construction |  |  |  |  | 2020-02-01 | On Time | 2027-03-01 | >6 month delay
T7130215 | Conversion of 10 R77E Locomotives | New York City Transit - Service Vehicles | Construction |  |  |  |  | 2020-09-01 | 4-6 month delay | 2024-12-01 | On Time
T8130205 | Critical Systems Upgrade of Track Geometry Cars | New York City Transit - Service Vehicles | Construction |  |  |  |  | 2023-09-01 |  | 2027-06-01
T8130206 | Purchase 45 Flat Cars | New York City Transit - Service Vehicles | Construction |  |  |  |  | 2022-07-01 | On Time | 2026-11-01 | >6 month delay
T8130208 | Non-Revenue Vehicles 2023 | New York City Transit - Service Vehicles | Construction |  |  |  |  | 2023-03-01 |  | 2027-03-01
T8100417 | Component Repairs: 207 St Overhaul Facility | New York City Transit - Shops & Yards | Construction | 2020-01-01 | On Time | 2021-11-01 | On Time | 2022-12-01 | On Time | 2025-04-01 | On Time
T8100418 | Yard Lighting at Fresh Pond Yard | New York City Transit - Shops & Yards | Construction |  |  |  |  | 2023-12-01 |  | 2025-07-01
T8100419 | Jamaica Yard Expansion Phase 1 - Design Only | New York City Transit - Shops & Yards | Design | 2023-01-01 | On Time | 2024-07-01 | >6 month delay
T8100420 | Yard Track - 2023 | New York City Transit - Shops & Yards | Construction |  |  |  |  | 2024-01-01 | On Time
T8100421 | Yard Switches - 2023 | New York City Transit - Shops & Yards | Construction |  |  |  |  | 2023-11-01 | On Time | 2024-06-01
T8100423 | Westchester Yard Drainage Improvements | New York City Transit - Shops & Yards | Planning |  |  |  |  | 2025-03-01 |  | 2029-03-01
T8100424 | Yard Fencing at Fresh Pond Yard | New York City Transit - Shops & Yards | Construction |  |  |  |  | 2023-12-01 |  | 2025-07-01
T6100408 | Replace Heavy Shop Equipment | New York City Transit - Shops And Yards | Construction | 2012-08-01 | On Time | 2015-07-01 | >6 month delay | 2015-07-01 | >6 month delay | 2025-12-01 | >6 month delay
T6100425 | Upgrade 207 St Overhaul Shop Equipment | New York City Transit - Shops And Yards | Construction |  |  |  |  | 2014-06-01 | >6 month delay | 2024-06-01 | >6 month delay
T6100439 | Purchase of Overhead Crane for Concourse Maintenance Facility | New York City Transit - Shops And Yards | Construction |  |  |  |  | 2017-04-01 | On Time | 2024-06-01 | >6 month delay
T6100453 | Purchase and Installation of a 2-Ton Overhead Crane at 207th Street Maintenance Facility | New York City Transit - Shops And Yards | Construction |  |  |  |  | 2017-04-01 | On Time | 2024-06-01 | >6 month delay
T7100408 | Upgrade Atlantic Avenue Cable Shop - Phase 1 - Design Only | New York City Transit - Shops And Yards | Design | 2022-01-01 | >6 month delay | 2024-05-01 | >6 month delay
T7100441 | New Railcar Receiving Facility | New York City Transit - Shops And Yards | Construction | 2018-09-01 | On Time | 2019-05-01 | On Time | 2023-01-01 | >6 month delay | 2025-02-01 | >6 month delay
T7100443 | DCE Car Washer Component Repairs at Canarsie & Jamaica - Design Only | New York City Transit - Shops And Yards | Design | 2019-07-01 | On Time | 2024-06-01 | >6 month delay
T8080317 | SigMod: Queens Blvd East and 3 Interlockings (Hillside) - Furnish | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2021-12-01 | On Time | 2026-07-01 | On Time
T8080318 | SigMod: Queens Blvd East and 3 Interlockings (Hillside) - Install | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2021-12-01 | On Time | 2026-07-01 | On Time
T8080323 | SigMod: Crosstown Line and 3 Interlockings | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2022-12-01 | On Time | 2027-09-01 | On Time
T8080328 | Interlocking SSI Replacement: Bergen Street on the Culver Line | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2022-12-01 | On Time | 2027-09-01 | On Time
T8080329 | CBTC: Equip 437 R211 Option 2 Cars | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-11-01
T8080331 | CBTC: Carborne Equipment Purchase | New York City Transit - Signals & Communication | Design |  |  |  |  | 2019-03-01 |  | 2024-03-01
T8080602 | Phone PBX Switch Upgrades at Jay St | New York City Transit - Signals & Communication | Design | 2022-05-01 |  | 2024-02-01 |  | 2024-04-01
T8080612 | Passenger ID CCTV at 88 Locations | New York City Transit - Signals & Communication | Construction | 2019-10-01 | On Time | 2021-05-01 | On Time | 2022-03-01 | On Time | 2024-11-01 | >6 month delay
T8080614 | Under River Tubes (URT) Security, Phase 3 | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2022-12-01 | On Time | 2026-12-01 | On Time
T8080615 | Liftnet Transition to Ethernet, Phase 2 - Package 1 | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-08-01 | >6 month delay
T8080616 | Liftnet Transition to Ethernet, Phase 2 - Package 2 | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2022-08-01 | On Time | 2025-01-01 | >6 month delay
T8080624 | PA/CIS Upgrade on the Canarsie Line, Phase 2 | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-12-01 |  | 2026-10-01
T8080640 | Antenna Cable Replacement on the Concourse Line | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-03-01 | On Time
T8080641 | Upgrade of Asynchronous Fiber Optic Network to SONET, Ring F | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-03-01 | >6 month delay
T8080646 | Laser Intrusion Detection | New York City Transit - Signals & Communication | Design | 2023-03-01 | 4-6 month delay | 2024-03-01 | >6 month delay | 2024-08-01 | 4-6 month delay
T8080647 | Track Intrusion Detection | New York City Transit - Signals & Communication | Design | 2023-03-01 | On Time | 2024-02-01 | On Time | 2024-07-01 | On Time
T8080649 | PSLAN Upgrade: 75 Street-Elderts Lane on the Jamaica Line | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-11-01 | 4-6 month delay
T8080650 | Passenger ID CCTV: Additional Locations | New York City Transit - Signals & Communication | Construction | 2022-08-01 | On Time | 2023-08-01 | On Time | 2023-12-01 | On Time | 2026-12-01 | On Time
T8080651 | Fiber Optic Cable Replacement (2022) | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2022-09-01 | On Time | 2024-04-01 | 4-6 month delay
T8080656 | PSLAN Upgrades for PA/CIS Phase 0 Stations | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-06-01 |  | 2025-05-01
T8080657 | Upgrade Asynchronous Fiber Optic Network to SONET, Ring E | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-12-01
T8080658 | Fiber Optic Cable Replacement (2023) | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-07-01 |  | 2025-12-01
T8080659 | Antenna Cable Replacement: Jay Street | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-09-01 |  | 2025-09-01
T8080660 | Comm Room Upgrade: APC Replacement | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-12-01
T8080661 | Comm Room HVAC: 138 Street-Grand Concourse on the Jerome Line | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-12-01
T8080664 | Connection Oriented Ethernet (COE), Phase 3C | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-12-01 |  | 2028-12-01
T8080665 | Fiber Optic Cable Replacement (A-cable) | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-12-01 |  | 2025-12-01
T8080666 | Fiber Optic Cable Replacement (B-cable) | New York City Transit - Signals & Communication | Construction |  |  |  |  | 2023-12-01 |  | 2025-12-01
T6080319 | Install Communication-Based Train Control on the Queens Boulevard Line West - Phase 1 | New York City Transit - Signals & Communications | Construction | 2013-10-01 | >6 month delay | 2016-02-01 | >6 month delay | 2015-08-01 | >6 month delay | 2024-12-01 | >6 month delay
T6080336 | Cathodic Protection (Steinway Tube) | New York City Transit - Signals & Communications | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-04-01 | On Time
T6080337 | Walkway for 8 Bridges on the Dyre Line | New York City Transit - Signals & Communications | Construction |  |  |  |  | 2022-05-01 | On Time | 2025-01-01 | On Time
T6080623 | Passenger Station Local Area Network at 68 Stations | New York City Transit - Signals & Communications | Construction | 2011-04-01 | On Time | 2014-06-01 | >6 month delay | 2016-09-01 | >6 month delay | 2024-01-01 | >6 month delay
T6080656 | Replace Server Hardware at the Rail Control Center and the Backup Control Center | New York City Transit - Signals & Communications | Construction |  |  |  |  | 2016-02-01 | On Time | 2024-05-01 | >6 month delay
T7080304 | Install Communication-Based Train Control (CBTC) on the 8 Avenue Line from 59 Street to High Street | New York City Transit - Signals & Communications | Construction | 2016-09-01 | On Time | 2018-11-01 | On Time | 2020-01-01 | On Time | 2025-01-01 | On Time
T7080307 | Modernize Signal Interlocking at Ditmas Avenue on the Culver Line | New York City Transit - Signals & Communications | Construction | 2016-04-01 | On Time | 2018-04-01 | On Time | 2019-02-01 | On Time | 2024-08-01 | >6 month delay
T7080327 | Life Cycle Modification of Speed Enforcement Systems | New York City Transit - Signals & Communications | Construction | 2017-08-01 | On Time | 2019-06-01 | On Time | 2020-08-01 | On Time | 2024-03-01 | On Time
T7080332 | Install Communication-Based Train Control (CBTC) from Church Avenue to West 8 Street on the Culver Line | New York City Transit - Signals & Communications | Construction | 2016-04-01 | On Time | 2018-11-01 | On Time | 2019-02-01 | On Time | 2024-08-01 | >6 month delay
T7080333 | Modernize Signal Interlocking at Avenue X on the Culver Line | New York City Transit - Signals & Communications | Construction | 2016-04-01 | On Time | 2018-04-01 | On Time | 2019-02-01 | On Time | 2024-08-01 | >6 month delay
T7080335 | Modernize 2 Signal Interlockings: 30 Street and 42 Street North on the 8 Avenue Line | New York City Transit - Signals & Communications | Construction | 2016-04-01 | On Time | 2018-11-01 | On Time | 2020-01-01 | On Time | 2025-01-01 | On Time
T7080342 | CBTC: Carborne Equipment Purchase | New York City Transit - Signals & Communications | Construction |  |  |  |  | 2019-03-01 | On Time | 2024-12-01 | >6 month delay
T7080343 | Mainline Switch Replacement on the CBTC Culver Line | New York City Transit - Signals & Communications | Construction |  |  |  |  | 2019-02-01 | On Time | 2024-08-01 | >6 month delay
T7080344 | Mainline Switch Replacement on the CBTC 8 Avenue Line | New York City Transit - Signals & Communications | Construction |  |  |  |  | 2020-01-01 | On Time | 2025-01-01 | On Time
T7080350 | Install Communication-Based Train Control on the Queens Boulevard Line West - Phase 1 | New York City Transit - Signals & Communications | Construction |  |  |  |  | 2015-08-01 | On Time | 2024-12-01 | >6 month delay
T7080607 | UHF T-Band Radio System Replacement | New York City Transit - Signals & Communications | Construction | 2016-10-01 | On Time | 2019-04-01 | On Time | 2023-01-01 | >6 month delay | 2024-04-01 | 4-6 month delay
T7080619 | Communication Room Upgrade and Expansion - Phase 2 (SBDP) - Design Only | New York City Transit - Signals & Communications | Design | 2017-08-01 | On Time | 2024-05-01 | On Time
T7080648 | Police Radio System: Enhanced Coverage (Steinway Tube) | New York City Transit - Signals & Communications | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-04-01 | On Time
T7080653 | Installation of Passenger Identification Cameras at Various Stations (SBDP) - Design Only | New York City Transit - Signals & Communications | Design | 2019-10-01 | On Time | 2024-08-01 | >6 month delay
T7010101 | Purchase 440 B-Division Railcars | New York City Transit - Subway Cars | Construction | 2012-12-01 | On Time | 2018-02-01 | On Time | 2018-02-01 | On Time | 2025-02-01 | >6 month delay
T7010102 | Purchase 20 B-Division Railcars - Open Gangway | New York City Transit - Subway Cars | Construction |  |  |  |  | 2018-02-01 | On Time | 2024-06-01 | >6 month delay
T7010104 | Upgrade 1030 A-Division R142 Railcars - Design Only | New York City Transit - Subway Cars | Design | 2018-06-01 | On Time | 2024-12-01 | >6 month delay
T7010105 | Purchase 1178 A-Division Railcars - Design Only | New York City Transit - Subway Cars | Design | 2018-06-01 | On Time | 2024-12-01 | >6 month delay
T8010102 | Purchase 640 B-Division Cars (R211 Option 1) | New York City Transit - Subway Cars | Construction |  |  |  |  | 2022-11-01 | On Time | 2027-01-01 | On Time
T70502A3 | Mainline Track / Myrtle Line (RF-U69 Plates) | New York City Transit - Track | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-04-01 | 4-6 month delay
T8050208 | Mainline Track Replacement 2020 / Flushing | New York City Transit - Track | Construction |  |  |  |  | 2020-02-01 | On Time | 2024-07-01 | >6 month delay
T8050218 | Mainline Track Replacement 2020 / West End | New York City Transit - Track | Construction |  |  |  |  | 2021-01-01 | On Time | 2024-03-01 | >6 month delay
T8050232 | Mainline Track Replacement 2021 / Jamaica | New York City Transit - Track | Construction |  |  |  |  | 2021-01-01 | On Time | 2024-03-01 | >6 month delay
T8050234 | Mainline Track Replacement 2021 / Jerome | New York City Transit - Track | Construction |  |  |  |  | 2021-06-01 | On Time | 2024-02-01 | >6 month delay
T8050237 | Mainline Track Replacement 2021 / Lenox-White Plains Road | New York City Transit - Track | Construction |  |  |  |  | 2021-08-01 | On Time | 2024-05-01 | >6 month delay
T8050241 | Mainline Track Replacement (Direct Fixation) / Jamaica | New York City Transit - Track | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-04-01 | 4-6 month delay
T8050242 | Mainline Track Replacement (Direct Fixation) / 63 Street | New York City Transit - Track | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-04-01 | 4-6 month delay
T8050244 | Mainline Track Replacement / 68 St-Hunter College | New York City Transit - Track | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-12-01 | On Time
T8050246 | Mainline Track Replacement / Westchester Square on the Pelham Line | New York City Transit - Track | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-09-01 | On Time
T8050250 | Mainline Track Replacement 2022 / Brighton | New York City Transit - Track | Construction |  |  |  |  | 2022-06-01 | On Time | 2024-04-01 | >6 month delay
T8050251 | Mainline Track Replacement 2022 / Support Costs | New York City Transit - Track | Construction | 2022-01-01 | On Time |  |  | 2022-01-01 | On Time | 2024-06-01 | On Time
T8050252 | Mainline Track Replacement 2022 / Myrtle | New York City Transit - Track | Construction |  |  |  |  | 2022-05-01 | On Time | 2024-02-01 | >6 month delay
T8050258 | Mainline Track Replacement 2022 / Liberty | New York City Transit - Track | Construction |  |  |  |  | 2022-06-01 | On Time | 2024-04-01 | >6 month delay
T8050266 | Mainline Track Replacement 2022 / White Plains Road | New York City Transit - Track | Construction |  |  |  |  | 2022-10-01 | On Time | 2024-02-01 | On Time
T8050268 | Mainline Track Replacement 2023 / 6th Ave-Culver | New York City Transit - Track | Construction |  |  |  |  | 2023-01-01 | On Time | 2025-03-01 | >6 month delay
T8050269 | Continuous Welded Rail 2023 | New York City Transit - Track | Construction |  |  |  |  | 2023-01-01 | On Time | 2024-08-01
T8050274 | Mainline Track Replacement 2023 / Astoria | New York City Transit - Track | Construction |  |  |  |  | 2023-04-01 | On Time | 2025-01-01 | 4-6 month delay
T8050275 | Mainline Track Replacement 2023 / Brighton | New York City Transit - Track | Construction |  |  |  |  | 2023-08-01 | On Time | 2025-02-01
T8050276 | Mainline Track Replacement 2023 / Jamaica | New York City Transit - Track | Construction |  |  |  |  | 2024-01-01 | On Time | 2024-12-01
T8050277 | Mainline Track Replacement 2023 / Canarsie | New York City Transit - Track | Construction |  |  |  |  | 2023-07-01 | On Time | 2024-12-01 | On Time
T8050279 | Mainline Track Replacement 2023 / Lenox-WPR | New York City Transit - Track | Construction |  |  |  |  | 2023-08-01 | On Time | 2024-09-01
T8050282 | Mainline Track Replacement 2023 / Rockaway | New York City Transit - Track | Construction |  |  |  |  | 2024-03-01 | >6 month delay
T8050284 | Mainline Track Replacement 2023 / 4th Avenue | New York City Transit - Track | Construction |  |  |  |  | 2023-04-01 | On Time | 2024-06-01 | On Time
T8050285 | Mainline Track Replacement 2023 / Flushing | New York City Transit - Track | Construction |  |  |  |  | 2023-10-01 | On Time | 2024-03-01
T8050286 | 2023 Track Force Account | New York City Transit - Track | Construction |  |  |  |  | 2023-07-01 |  | 2024-06-01
T8050287 | Mainline Track Replacement at 3 Stations | New York City Transit - Track | Construction |  |  |  |  | 2023-12-01 |  | 2026-12-01
T8050288 | Mainline Track Replacement at Broadway Junction on the Jamaica Line | New York City Transit - Track | Construction |  |  |  |  | 2023-12-01 |  | 2027-09-01
T8050289 | Mainline Track Replacement 2023 / White Plains Road | New York City Transit - Track | Construction |  |  |  |  | 2023-08-01 |  | 2024-03-01
T8050290 | Mainline Track Replacement 2023 / Broadway (Canal St) | New York City Transit - Track | Construction |  |  |  |  | 2023-10-01 |  | 2024-06-01
T8050294 | Mainline Track Replacement 2024 / White Plains Road | New York City Transit - Track | Construction |  |  |  |  | 2024-01-01
T8050295 | Mainline Track Replacement 2024 / Jamaica | New York City Transit - Track | Construction |  |  |  |  | 2024-01-01
T8050321 | SigMod: Queens Blvd East (Hillside) - Switch Replacement | New York City Transit - Track | Construction |  |  |  |  | 2021-12-01 | On Time | 2026-07-01 | On Time
T8050322 | Mainline Track Switches 2022 / Support Costs | New York City Transit - Track | Construction | 2022-01-01 | On Time |  |  | 2022-01-01 | On Time | 2024-06-01 | On Time
T8050324 | Mainline Track Switches 2022 / 8th Avenue | New York City Transit - Track | Construction |  |  |  |  | 2022-05-01 | On Time | 2024-03-01 | >6 month delay
T8050328 | Mainline Track Switches 2022 / Brighton | New York City Transit - Track | Construction |  |  |  |  | 2022-10-01 | On Time | 2024-04-01 | >6 month delay
T8050336 | Mainline Track Switches 2023 / 8th Ave-Fulton | New York City Transit - Track | Construction |  |  |  |  | 2023-08-01 | On Time | 2025-04-01
T8050338 | Mainline Track Switches 2023 / Lenox-WPR | New York City Transit - Track | Construction |  |  |  |  | 2023-12-01 | On Time | 2024-06-01
T8050339 | Mainline Track Switches 2023 / Rockaway | New York City Transit - Track | Construction |  |  |  |  | 2023-08-01 | On Time | 2024-06-01 | On Time
T8050340 | Mainline Track Switches 2023 / Sea Beach | New York City Transit - Track | Construction |  |  |  |  | 2023-03-01 | On Time | 2024-03-01 | On Time
T8050341 | Mainline Track Switches 2023 / Myrtle | New York City Transit - Track | Construction |  |  |  |  | 2023-05-01 | On Time | 2024-01-01 | On Time
T7090202 | Renewal of Avenue Z Substation on the Culver Line | New York City Transit - Traction Power | Construction | 2016-03-01 | On Time | 2017-08-01 | On Time | 2018-09-01 | On Time | 2024-07-01 | >6 month delay
T7090206 | Replace High Tension Switchgear at Various Locations | New York City Transit - Traction Power | Construction | 2016-02-01 | On Time | 2018-06-01 | On Time | 2018-12-01 | On Time | 2024-02-01 | >6 month delay
T7090219 | New Substation at Canal Street on the 8 Avenue Line | New York City Transit - Traction Power | Construction | 2017-08-01 | On Time | 2018-11-01 | On Time | 2022-09-01 | >6 month delay | 2025-08-01 | >6 month delay
T7090225 | Renewal of Washington Heights Substation on the 8 Avenue Line - Design Only | New York City Transit - Traction Power | Design | 2019-04-01 | On Time | 2024-03-01 | >6 month delay
T8090211 | Install Low-Resistance Contact Rail on the Jamaica Line | New York City Transit - Traction Power | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-04-01 | 4-6 month delay
T8090212 | New Negative Side Feeders on the Jamaica Line | New York City Transit - Traction Power | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-04-01 | 4-6 month delay
T8090213 | Install Low-Resistance Contact Rail on the 63 Street Line | New York City Transit - Traction Power | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-04-01 | 4-6 month delay
T8090214 | New Negative Side Feeders on the 63 Street Line | New York City Transit - Traction Power | Construction |  |  |  |  | 2021-12-01 | On Time | 2024-04-01 | 4-6 month delay
T8090215 | New Substation: 28 Street / 8 Avenue | New York City Transit - Traction Power | Construction |  |  |  |  | 2022-10-01 | On Time | 2025-09-01 | On Time
T8090216 | Replace Transformers and Associated Equipment: 1 Substation | New York City Transit - Traction Power | Construction |  |  |  |  | 2022-06-01 | On Time | 2024-02-01 | On Time
T8090217 | Replace Transformers and Associated Equipment at 2 Substations | New York City Transit - Traction Power | Construction |  |  |  |  | 2023-07-01 |  | 2025-07-01
T8090218 | Replace DC Lineup at Jamaica Yard Substation | New York City Transit - Traction Power | Construction |  |  |  |  | 2023-07-01 |  | 2025-07-01
T8090219 | Replace High Tension Switchgear at 5 Substations | New York City Transit - Traction Power | Construction |  |  |  |  | 2023-07-01 |  | 2025-07-01
T8090220 | Replace High Tension Switchgear at West 82 Street Substation | New York City Transit - Traction Power | Construction |  |  |  |  | 2023-07-01 |  | 2025-07-01
T8090221 | Substation Renewal: 13 Street / Culver | New York City Transit - Traction Power | Construction |  |  |  |  | 2023-04-01 |  | 2025-05-01
T8090222 | Substation Renewal: 82 Road / Queens Boulevard | New York City Transit - Traction Power | Construction |  |  |  |  | 2023-04-01 |  | 2025-05-01
T8090223 | Replace High Tension Switchgear at Seeley Street Substation | New York City Transit - Traction Power | Construction |  |  |  |  | 2023-04-01 |  | 2025-05-01
T8090406 | Upgrade SCADA System (BMT Division) | New York City Transit - Traction Power | Construction |  |  |  |  | 2022-08-01 | On Time | 2025-08-01 | On Time
T8090410 | Installation of Second Negative Rail on the Dyre Line | New York City Transit - Traction Power | Construction |  |  |  |  | 2022-12-01 | On Time | 2024-04-01 | On Time
T8090411 | Rehabilitation of 5 CBHs at Various Locations | New York City Transit - Traction Power | Construction |  |  |  |  | 2022-12-01 | On Time | 2025-06-01 | On Time
T8090412 | Emergency Alarms, Phase 1 | New York City Transit - Traction Power | Construction |  |  |  |  | 2023-12-01 |  | 2028-06-01